## Ark1
Gantt-Chart | Planning |  |  |  |  | Design and content |  |  |  |  | Developing |  |  |  |  | Result
Lofthus frukt og saft | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4
Project start | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20
Frontend-developer | Meeting with
and customer | customer
Frontend-developer |  | Meeting with
and designer |  | designer
Frontend-developer |  |  | Research
and designer
Frontend-developer |  |  |  | Strategic planning
and designer
Frontend-developer |  |  |  |  | Meeting with
and copywriter |  |  |  |  | copywriter
Designer | [5 empty] | Styletile
Frontend-developer | [7 empty] | Site structure
and designer
Copywriter | [6 empty] | Text content
Photographer | [7 empty] | Taking and editing pictures
Frontend-developer | [10 empty] | Wireframe
Frontend-developer | [11 empty] | Coding and site build
Frontend-developer | [15 empty] | Meeting with
and customer | [15 empty] | customer
Frontend-developer | [16 empty] | Testing and validating
Frontend-developer, | [18 empty] | Adjustment
designer and copywriter
Frontend-developer, | [19 empty] | Launch
customer, designer
and copywriter